## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed) | X-team | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page. | Pass | DB, 10/28/2024, we have it so that the user will not need to navigate to the Needs page when they have logged in; it will already be visible to them. |  |  | Pass | GS, 11/7/2024
| Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page. | Pass | DB, 10/28/2024, same explanation as above. |  |  | Pass | GS, 11/7/2024
| Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute. | Fail | DB, 10/28/2024, do not have a message display if there are no needs available to contribute |  |  | Fail | GS, 11/7/2024, Message is not persistant, is populated at first but disapears at reload/rerout
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | DB, 10/28/2024 |  |  | Pass | GS, 11/7/2024
| Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Fail | DB, 10/28/2024, there is a button present on the Angular side, but it doesn't work with the back-end code, may have to do with mapping of userController, which was also an issue with the login. |  |  | Pass | GS, 11/7/2024
As a HELPER I want to have a funding basket where I can save the needs so that I can check out multiple needs at the same time. | Given I am a U-fund manager when I try to access a funding basket then I am unable to do so. | Pass | KG, 10/28/2024, on the Angular side, the admin is taken to a blank page |  |  | Pass | GS, 11/7/2024
| Given I am a Helper when I log onto the website then I should have a personal funding basket. | Pass | KG, 10/28/2024 |  |  | Pass | GS, 11/7/2024
As a user I want to be able to login so that I can access the rest of the website. | Given I login as 'admin', when I press the login button, then I should access the manager page. | Pass | LM, 10/28/2024, |  |  | Fail | GS, 11/7/2024, Login page will route you to a helper named 'admin' instead of manager page
| Given I login as one of the premade users, when I press the login button, then I should access the Helper page. | Fail | DB, 10/28/2024, doesn't currently work, seems to be an issue with the overall mapping of the back-end, as inputting 'admin' as a username gets the admin page. |  |  | Pass | GS, 11/7/2024
| Given I login as a non-existent user, when I press the login button, then I should be denied access. | Pass | LM, 10/28/2024, |  |  | Pass | GS, 11/7/2024
As a helper, I want to be able to remove needs from my funding basket so I can won’t checkout needs I do not want to fund. | Given there is a need in my funding basket, when I choose to remove a need, then the need should no longer be in my funding basket and should not be funded during checkout. | Fail | JA, 10/29/24, cannot currently access the funding basket (ON MAIN). There is a feature branch which has this functionality. |  |  | Pass | GS, 11/7/2024
As a Helper I want to add a need to my funding basket so I can select what needs I bring to checkout. | Given a user has identified a need, when the user adds the need to the basket, then the need should be visible in the basket for checkout. | Fail | KKS, 10/28/2024; Does not work on the UI side, api throws the exception that 'Request method 'POST' not supported'. I assume somewhere there is a method that is trying to GET the POST request to update the user basket |  |  | Pass | GS, 11/7/2024
| Given a user has identified a need already in their basket when the user attempts to add the need to the basket then an error message should inform the user that the addition is a duplicate and the action was not completed. | Fail | KKS, 10/28/2024; Cannot be tested until previous issue is fixed. Also needs to be tested on the API side. |  |  | Pass | GS, 11/7/2024
As a User I want to be able to select multiple needs at once so that I can move multiple needs easily. | Given I am a Helper and I can see the need list when I choose multiple needs then I can add them to my funding basket. | Fail | JA, 10/29/24, The needs list is visible, but you cannot currently select multiple needs to add them to the basket
| Given I am a Helper and I have more than one need in my funding basket when I choose multiple needs then I can interact with all of them. | Fail | JA, 10/29/24, you cannot currently add needs to the funding basket (ON MAIN).
| Given I am an Admin and I have more than one need in my need cupboard when I choose multiple needs then I can interact with all of them. | Fail | JA, 10/29/24, you cannot currently select multiple needs as an Admin.
As a Helper I want to send a message to admin so that I can suggest needs for the admin to create. | Given I am a helper when I send a message to the admin then I expect them to get the message on their message board.
Given I am an admin when I login to the website then I should expect to see the pre-existing messages as well as the new messages on my message board.
Given I am an admin when I have no messages in my message board then it should be completely empty.